QToN No. 6

Committee Support

LEGISLATIVE ASSEMBLY

FOR THE AUSTRALIAN CAPITAL TERRITORY

Standing Committee on Health and Community Wellbeing

# Inquiry into Annual and Financial Reports 2021-2022

# ANSWER TO QUESTION TAKEN ON NOTICE

Asked by MR JAMES MILLIGAN MLA on 1 November 2022: MS KALENA SMITHAM took on notice the following question(s):

Reference: Hansard uncorrected proof transcript 1 November 2022 Page 25

In relation to:

Regarding paediatric reviews how much are the road map and recommendations for each service have you completed since the last review?

MINISTER STEPHEN-SMITH MLA:  The answer to the Member’s question is as follows:–

Paediatric Organisational and Service Plan 2021-2023 – Roadmap for Year One

| Action | Status |
| --- | --- |
| Plan sign-off | Completed |
| Agree future governance | Completed |
| Recruit Project Coordinators | Completed |
| Team Readiness & Culture – including interprofessional working | Completed |
| Agree outcomes and baseline | Progressing |
| Complete detailed financial modelling & rebaseline | Progressing |
| Interprofessional handovers and huddles | Completed |
| Interprofessional unit leadership & job plan expectations | Completed |
| Formalise outpatient protocols | Progressing |
| Formalise arrangements for the critically-ill/deteriorating child | Completed |
| Review nursing ward allocations and expenditure | Completed |
| Complete training needs analysis and capability assessments | Progressing |
| Implement improved communications with VMOs | Progressing |
| Initiate cross-directorate work for children in the community | Completed |
| Complete detailed staffing estimates and profiles | Progressing |
| Finalise consultation and implementation planning | Progressing |
| Recruit to staff specialist, nursing & allied health positions | Progressing |
| Define Allied Health & Specialist Nursing Care Pathways | Progressing |
| Implement case management working across the service | Completed |
| Revised Business Case for Level 1 PICU | Progressing (through Clinical Services Building project) |
| Develop detailed roadmap and actions for Year 2 | Progressing |
| Develop prospective and retrospective business cases for other key service changes | Progressing |
| Implement revised Blue Star & Gender Dysphoria Service | Progressing |
| Implement revised community pathway in full | Completed |
| Revise ROMAC policy | Progressing |
| Finalise SLA with SCHN | Progressing |

Approved for circulation to the Standing Committee on Health and Community Wellbeing Signature: Date: By the Minister for Health, Ms Rachel Stephen-Smith MLA